## Team
Initials | First Name | Last Name | Email | Github Username
sa | Sarthak | Ahir | sahir@stevens.edu | ahirsarthak
rb | Roshan | Badgujar | rbadguja@stevens.edu | badgujar-rosh7
sp | Shashwat | Prabhat | sprabhat@stevens.edu | ShashwatPrabhat
sr | Srikar | Reddy | sgundam@stevens.edu | srikar104
as | Akshay | Sahasrabuddhe | asahasra@stevens.edu | akshay-sahasrabuddhe
GitHub Repository:- |  | https://github.com/akshay-sahasrabuddhe/agile-army

## Backlog
Id | Title | Acceptance test | Owner | Status
US01 | Navigation Section | navigation() | as | Completed
US02 | Footer Section | footer() | rb | Completed
US03 | Home Page Slider Section | homePageSlider() | sp | Completed
US04 | Home Page Image Buttons Section | imageButton() | sr | Completed
US05 | Home Page Reviews Slider Section | homePageReviewSlider() | sa | Completed
US06 | Home Page Reviews Slider Section | guitarImageButtons() | as,rb,sp,sr,sa | Completed

## Burndown
Sprint 1 | Date | Remaining Stories | Actual Stories | Story Velocity | LOC | Mins | Code Velocity
Start | 17 Feb - 22 Mar | 15 | 15 | 0 | 0 | 0 | 0
Sprint 1 | 22 Feb - 02 Mar | 10 | 5 | 5 | 560 | 5680 | 5.9154
Sprint 2 | 03 Mar - 24 Mar | 9 | 1 | 5 | 1175 | 6000 | 11.75

## Stories
Id | Title | Acceptance test | Priority | Story points | Description
US01 | Navigation Section | navigation() | 1 | 1 | As a user, I want to navigate through each nav item on the webpage. So, that I will able to view each webpage which is linked to that specific webpage.
US02 | Footer Section | footer() | 1 | 1 | As a user, I want to click on the links listed in the footer. So, that I will able to visit the specific webpage which is related that respective link.
US03 | Home Page Slider Section | homePageSlider() | 2 | 1 | As a user, I want to view the image slides of each game which is listed in the game portal. So, that I can decide which game should I choose to play.
US04 | Home Page Image Buttons Section | imageButton() | 2 | 1 | As a user, I want to view the image buttons of each game which is listed in the game portal. So, that I can click on any one image button to play a game.
US05 | Home Page Reviews Slider Section | homePageReviewSlider() | 3 | 1 | As a user, I want to view the card slider of the reviews that are posted by all users. So, that based the recent reviews that are posted by the people, I can decide which game is most popular.
US06 | Guitar Game Image Buttons | guitarImageButtons() | 4 | 1 | As a user, I want to click on the image buttons on the webpage and play a guitar. So, that I can hear a music which is played by me.
US07 | Sidebar Section | paintApplicationSidebar() | 5 | 1 | As a user, I want to view the sidebar which includes options like "brush color","background color", "size", "pen style", "save and clear" buttons. So, that with help of this sidebar, I can paint on canvas.
US08 | Canvas Section | paintApplicationCanvas() | 6 | 1 | As a user, I want to use the canvas. So, that with help of this canvas, I can paint any picture.
US09 | Guess The Gibberish Image Buttons Section | guessTheGibberishCategories() | 7 | 1 | As a user, I want to view all the catagories which are listed in "guess the gibberish" game. So, that I can select any one category to play this game.
US10 | Guess The Gibberish Card Section | guessTheGibberishWordCard() | 8 | 1 | As a user, I want to view a gibberished word on the card. So, that I can guess its answer and submit it by entering the answer in a textbox.
US11 | Guess The Gibberish User Score Notification | guessTheGibberishScoreCounter() | 9 | 1 | As a user, I want to view my total score. So, that I can see that how much can I score in a single session.
US12 | Guess The Gibberish Score List | guessTheGibberishHighScorer() | 10 | 1 | As a user, I want to view the list of all the users who played this game and the sores of respective users as well. So, that I can see my rank in the list.
US15 | Signup Section | userSignup() | 11 | 1 | As a user, I want to register myself for this web application. So, that I can login to this application.
US16 | Login Section | userLogin() | 12 | 1 | As a user, I want to login to this web application. So, that I can play all the games that are included in this web application.
US17 | User Profile Section | userProfile() | 13 | 1 | As a user, I want to view my user profile. So, that I can write some reviews for the games.

## Sprint 1
Id | Title | Owner | Status | Estimated Size | Estimated Time(Mins.) | Actual Size | Actual Time | Complete
US01 | Navigation Section | as | Done | 100 | 960 | 90 | 480 | 2022-03-01
T01.01 | Animation of Navigation Section | as | Done | 100 | 640 | 30 | 640 | 2022-03-02
US02 | Footer Section | rb | Done | 100 | 960 | 60 | 480 | 2022-03-01
T02.01 | Animation of Footer Section | rb | Done | 100 | 640 | 30 | 240 | 2022-03-02
US03 | Home Page Slider Section | sp | Done | 150 | 480 | 60 | 960 | 2022-03-02
T03.01 | Animation of Home Page Section | sp | Done | 100 | 480 | 20 | 240 | 2022-03-03
US04 | Home Page Image Buttons Section | sr | Done | 80 | 480 | 100 | 960 | 2022-03-03
T04.01 | Animation of Home Page Image Buttons Section | sr | Done | 100 | 480 | 50 | 240 | 2022-03-03
US05 | Home Page Reviews Slider Section | sa | Done | 200 | 960 | 100 | 960 | 2022-03-02
T05.01 | Animation of Home Page Reviews Slider Section | sa | Done | 100 | 480 | 20 | 480 | 2022-03-03
Review Results:-
Things that we want to keep doing:-
1. While working on github, make use of individual branches.
2. Make the use of backup branch.
Things that we want to avoid doing in the future:-
1. Avoid to change the webpage flow at the last moment
2. Avoid to use inline stylesheets

## Sprint 2
Id | Title | Owner | Status | Estimated Size | Estimated Time(Mins.) | Actual Size | Actual Time | Complete
T06.01 | Include the guitar game's tab in navigation and footer with animation | sp | Done | 100 | 640 | 90 | 480 | 2022-03-22
T06.02 | Writing HTML Structure for Electric guitar | sp | Done | 150 | 480 | 100 | 480 | 2022-03-23
T06.03 | Writing CSS Structure for Electric guitar | rb | Done | 100 | 480 | 200 | 960 | 2022-03-23
T06.04 | Writing Scripts in JS for Electric guitar | rb | Done | 100 | 480 | 180 | 480 | 2022-03-23
T06.05 | Writing HTML Structure for normal guitar | as | Done | 100 | 960 | 40 | 240 | 2022-03-22
T06.06 | Writing CSS Structure for Normal guitar | as | Done | 100 | 640 | 50 | 480 | 2022-03-22
T06.07 | Writing Scripts in JS for Normal guitar | as | Done | 100 | 640 | 275 | 960 | 2022-03-22
T06.08 | Animation of guitar strings structure | sr | Done | 80 | 480 | 50 | 240 | 2022-03-24
T06.09 | Animation of guitar buttons | sr | Done | 100 | 480 | 100 | 960 | 2022-03-24
T06.10 | Writing HTML Structure for Page Background and Text(includes heading, subheading etc.) | sa | Done | 200 | 240 | 50 | 240 | 2022-03-24
T06.11 | Writing CSS Structure for Page Background and Text(includes heading, subheading etc.) | sa | Done | 100 | 320 | 40 | 480 | 2022-03-24
Review Results:-
Things that we want to keep doing:-
1. While working on github, make use of individual branches.
2. Make the use of backup branch.
3. Drawing wireframes before starting development
Things that we want to avoid doing in the future:-
1. Avoid to spend more time on CSS
2. Avoid to use unwanted styles in the css file

## Sprint 3
Id | Title | Owner | Status | Estimated Size | Estimated Time(Mins.) | Actual Size | Actual Time | Complete
T07.01 | Writing HTML Structure for sidebar section | sp | Done | 100 | 640
T08.01 | Writing HTML Structure for sidebar section | sp | Done | 150 | 480
T07.02 | Writing CSS Structure for sidebar section | rb | Done | 100 | 480
T08.02 | Writing CSS Structure for canvas section | rb | Done | 100 | 480
T07.03 | Writing Scripts in JS for canvas section | as | Done | 100 | 960
T08.03 | Writing Scripts in JS for canvas section | as | Done | 100 | 640
T07.04 | Animation of sidebar section | sr | Done | 80 | 480
T08.04 | Animation of canvas section | sr | Done | 100 | 480
T07.05 | Writing HTML Structure for Page Background and Text(includes heading, subheading etc.) | sa | Done | 200 | 240
T08.05 | Writing CSS Structure for Page Background and Text(includes heading, subheading etc.) | sa | Done | 200 | 240

## Unit Test Cases
Id | Title | Acceptance test | Priority | Execution | Expected Result | Actual Result | Owner
US01 | Navigation Section | navigation() | 1 | Mannual | Navigation should appear at the top with all animations. | Navigation is successfully appearing at the top with all animations. | as
US02 | Footer Section | footer() | 2 | Mannual | Footer should appear at the bottom with all animations. | Footer is successfully appearing at the bottom with all animations. | rb
US03 | Home Page Slider Section | homePageSlider() | 3 | Mannual | An image slider should appear in the webpage body. | An image slider is successfully appearing in the webpage body. | sp
US04 | Home Page Image Buttons Section | imageButton() | 4 | Mannual | Image buttons should appear in the webpage body. | Image buttons are successfully appearing in the webpage body. | sr
US05 | Home Page Reviews Slider Section | homePageReviewSlider() | 5 | Mannual | A review slider should appear in the webpage body. | A review slider is successfully appearing in the webpage body. | sa
US06 | Navigation Section | guitarImageButtons() | 6 | Mannual | Guitar Game Navigation Item should appear at the top with all animations. | Guitar Game Navigation is successfully appearing at the top with all animations. | sp
US07 | Footer Section | guitarImageButtons() | 7 | Mannual | Guitar Game Footer should appear at the bottom with all animations. | Guitar Game Footer is successfully appearing at the bottom with all animations. | sr
US08 | Browser compatibility for normal guitar section | guitarImageButtons() | 8 | Mannual | User should be able to use normal guitar game in all screen resolutions | User is able to use normal guitar game in all screen resolutions | as
US09 | Browser compatibility for electric guitar section | guitarImageButtons() | 9 | Mannual | User should be able to use electric guitar game in all screen resolutions | User is able to use electric guitar game in all screen resolutions | rb
US10 | Animations for content | guitarImageButtons() | 10 | Mannual | A user should be able to view all animations applied to the content | A user is able to view all animations applied to the content | sa