## Team
Initials | First Name | Last Name | Email | Github Username
sa | Sarthak | Ahir | sahir@stevens.edu | ahirsarthak
rb | Roshan | Badgujar | rbadguja@stevens.edu | badgujar-rosh7
sp | Shashwat | Prabhat | sprabhat@stevens.edu | ShashwatPrabhat
sr | Srikar | Reddy | sgundam@stevens.edu | srikar104
as | Akshay | Sahasrabuddhe | asahasra@stevens.edu | akshay-sahasrabuddhe
GitHub Repository:- |  | https://github.com/akshay-sahasrabuddhe/agile-army

## Backlog
Id | Title | Acceptance test | Owner | Status
US01 | Navigation Section | navigation() | as | Completed
US02 | Footer Section | footer() | rb | Completed
US03 | Home Page Slider Section | homePageSlider() | sp | Completed
US04 | Home Page Image Buttons Section | imageButton() | sr | Completed
US05 | Home Page Reviews Slider Section | homePageReviewSlider() | sa | Completed
US06 | Home Page Reviews Slider Section | guitarImageButtons() | as,rb,sp,sr,sa | Completed
US07 | Sidebar Section | paintApplicationSidebar() | as,rb,sp,sr,sa | Completed
US08 | Canvas Section | paintApplicationCanvas() | as,rb,sp,sr,sa | Completed

## Burndown
Sprint 1 | Date | Remaining Stories | Actual Stories | Story Velocity | LOC | Mins | Code Velocity
Start | 17 Feb - 22 Mar | 15 | 15 | 0 | 0 | 0 | 0
Sprint 1 | 22 Feb - 02 Mar | 10 | 5 | 5 | 560 | 5680 | 5.9154
Sprint 2 | 03 Mar - 24 Mar | 9 | 1 | 1 | 1175 | 6000 | 11.75
Sprint 2 | 25 Mar - 4 Apr | 10 | 2 | 2 | 355 | 3880 | 5.4896

## Stories
Id | Title | Acceptance test | Priority | Story points | Description
US01 | Navigation Section | navigation() | 1 | 1 | As a user, I want to navigate through each nav item on the webpage. So, that I will able to view each webpage which is linked to that specific webpage.
US02 | Footer Section | footer() | 1 | 1 | As a user, I want to click on the links listed in the footer. So, that I will able to visit the specific webpage which is related that respective link.
US03 | Home Page Slider Section | homePageSlider() | 2 | 1 | As a user, I want to view the image slides of each game which is listed in the game portal. So, that I can decide which game should I choose to play.
US04 | Home Page Image Buttons Section | imageButton() | 2 | 1 | As a user, I want to view the image buttons of each game which is listed in the game portal. So, that I can click on any one image button to play a game.
US05 | Home Page Reviews Slider Section | homePageReviewSlider() | 3 | 1 | As a user, I want to view the card slider of the reviews that are posted by all users. So, that based the recent reviews that are posted by the people, I can decide which game is most popular.
US06 | Guitar Game Image Buttons | guitarImageButtons() | 4 | 1 | As a user, I want to click on the image buttons on the webpage and play a guitar. So, that I can hear a music which is played by me.
US07 | Sidebar Section | paintApplicationSidebar() | 5 | 1 | As a user, I want to view the sidebar which includes options like "brush color","background color", "size", "pen style", "save and clear" buttons. So, that with help of this sidebar, I can paint on canvas.
US08 | Canvas Section | paintApplicationCanvas() | 6 | 1 | As a user, I want to use the canvas. So, that with help of this canvas, I can paint any picture.
US09 | HTML header section | htmlHeaderSection() | 7 | 1 | As a user, I want to view all the normal buttons and dropdown buttons. So, that I can select any level from dropdown button and start playing the game.
US10 | HTML body section | htmlBodySection() | 8 | 1 | As a user, I want to view map for maze game. So, that I can move the object from the map and can reach to the final destination.
US11 | CSS header section | cssHeaderSection() | 9 | 1 | As a user, I want to view all the normal buttons and dropdown buttons in specific colors and catchy styles. So, that I can find any level from dropdown button and start playing the game.
US12 | CSS body section | cssBodySection() | 10 | 1 | As a user, I want to view map borders for maze game. So, that I can move the object from the map and can reach to the final destination.
US13 | JS header section | jsHeaderSection() | 11 | 1 | As a user, I want to select the level from the dropdown button. So, that when I click on start button the game should start according to the level which is selected in the dropdown button.
US14 | JS body section | jsBodySection() | 12 | 1 | As a user, I want to select the level from the dropdown button. So, that when I click on start button the maze game map should change according to the level which is selected in the dropdown button.
US15 | Animation header section | animationHeaderSection() | 13 | 1 | As a user, when page loads I should be able to see that all buttons from the webpage should slide from either left, right, top or bottom. So, that when the loading is completed I can see all the sections at their original and appropriate positions.
US16 | Animation body section | animationBodySection() | 14 | 1 | As a user, when page loads I should be able to see that the entire body section from the webpage should slide from either left, right, top or bottom. So, that when the loading is completed I can see all the sections at their original and appropriate positions.
US17 | HTML Page Background and Text Section | htmlPageBackgroundAndTextSection() | 15 | 1 | As a user, I want to see the information about the game. So, that this information can help me to play this game and I will be able to view some benefits of playing this game.
US18 | CSS Page Background and Text | cssPageBackgroundAndTextSection() | 16 | 1 | As a user, I want to see the information about the game in specific colors and catchy styles. So, I can view this information before playing this game.

## Sprint 1
Id | Title | Owner | Status | Estimated Size | Estimated Time(Mins.) | Actual Size | Actual Time | Complete
US01 | Navigation Section | as | Done | 100 | 960 | 90 | 480 | 2022-03-01
T01.01 | Animation of Navigation Section | as | Done | 100 | 640 | 30 | 640 | 2022-03-02
US02 | Footer Section | rb | Done | 100 | 960 | 60 | 480 | 2022-03-01
T02.01 | Animation of Footer Section | rb | Done | 100 | 640 | 30 | 240 | 2022-03-02
US03 | Home Page Slider Section | sp | Done | 150 | 480 | 60 | 960 | 2022-03-02
T03.01 | Animation of Home Page Section | sp | Done | 100 | 480 | 20 | 240 | 2022-03-03
US04 | Home Page Image Buttons Section | sr | Done | 80 | 480 | 100 | 960 | 2022-03-03
T04.01 | Animation of Home Page Image Buttons Section | sr | Done | 100 | 480 | 50 | 240 | 2022-03-03
US05 | Home Page Reviews Slider Section | sa | Done | 200 | 960 | 100 | 960 | 2022-03-02
T05.01 | Animation of Home Page Reviews Slider Section | sa | Done | 100 | 480 | 20 | 480 | 2022-03-03
Review Results:-
Things that we want to keep doing:-
1. While working on github, make use of individual branches.
2. Make the use of backup branch.
Things that we want to avoid doing in the future:-
1. Avoid to change the webpage flow at the last moment
2. Avoid to use inline stylesheets

## Sprint 2
Id | Title | Owner | Status | Estimated Size | Estimated Time(Mins.) | Actual Size | Actual Time | Complete
T06.01 | Include the guitar game's tab in navigation and footer with animation | sp | Done | 100 | 640 | 90 | 480 | 2022-03-22
T06.02 | Writing HTML Structure for Electric guitar | sp | Done | 150 | 480 | 100 | 480 | 2022-03-23
T06.03 | Writing CSS Structure for Electric guitar | rb | Done | 100 | 480 | 200 | 960 | 2022-03-23
T06.04 | Writing Scripts in JS for Electric guitar | rb | Done | 100 | 480 | 180 | 480 | 2022-03-23
T06.05 | Writing HTML Structure for normal guitar | as | Done | 100 | 960 | 40 | 240 | 2022-03-22
T06.06 | Writing CSS Structure for Normal guitar | as | Done | 100 | 640 | 50 | 480 | 2022-03-22
T06.07 | Writing Scripts in JS for Normal guitar | as | Done | 100 | 640 | 275 | 960 | 2022-03-22
T06.08 | Animation of guitar strings structure | sr | Done | 80 | 480 | 50 | 240 | 2022-03-24
T06.09 | Animation of guitar buttons | sr | Done | 100 | 480 | 100 | 960 | 2022-03-24
T06.10 | Writing HTML Structure for Page Background and Text(includes heading, subheading etc.) | sa | Done | 200 | 240 | 50 | 240 | 2022-03-24
T06.11 | Writing CSS Structure for Page Background and Text(includes heading, subheading etc.) | sa | Done | 100 | 320 | 40 | 480 | 2022-03-24
Review Results:-
Things that we want to keep doing:-
1. While working on github, make use of individual branches.
2. Make the use of backup branch.
3. Drawing wireframes before starting development
Things that we want to avoid doing in the future:-
1. Avoid to spend more time on CSS
2. Avoid to use unwanted styles in the css file

## Sprint 3
Id | Title | Owner | Status | Estimated Size | Estimated Time(Mins.) | Actual Size | Actual Time | Complete
T07.01 | Writing HTML Structure for sidebar section | sp | Done | 100 | 640 | 15 | 480 | 2022-04-01
T08.01 | Writing HTML Structure for canvas section | sp | Done | 150 | 480 | 15 | 480 | 2022-04-02
T07.02 | Writing CSS Structure for sidebar section | rb | Done | 100 | 480 | 60 | 640 | 2022-04-03
T08.02 | Writing CSS Structure for canvas section | rb | Done | 100 | 480 | 40 | 480 | 2022-04-03
T07.03 | Writing Scripts in JS for sidebar section | as | Done | 100 | 960 | 70 | 480 | 2022-04-04
T08.03 | Writing Scripts in JS for canvas section | as | Done | 100 | 640 | 30 | 240 | 2022-04-04
T07.04 | Animation of sidebar section | sr | Done | 80 | 480 | 25 | 120 | 2022-04-05
T08.04 | Animation of canvas section | sr | Done | 100 | 480 | 30 | 240 | 2022-04-06
T07.05 | Writing HTML Structure for Page Background and Text(includes heading, subheading etc.) | sa | Done | 200 | 240 | 40 | 240 | 2022-04-05
T08.05 | Writing CSS Structure for Page Background and Text(includes heading, subheading etc.) | sa | Done | 200 | 240 | 30 | 480 | 2022-04-06
Review Results:-
Things that we want to keep doing:-
1. While working on github, make use of individual branches.
2. Make the use of backup branch.
3. Drawing wireframes before starting development
4. Following best practices while wirting HTML and CSS structure
Things that we want to avoid doing in the future:-
1. Avoid to spend more time on drawing the wireframes

## Sprint 4
Id | Title | Owner | Status | Estimated Size | Estimated Time(Mins.) | Actual Size | Actual Time | Complete
US09 | Writing HTML Structure for header section | sp | Done | 50 | 480
US10 | Writing HTML Structure for body section | sp | Done | 50 | 480
US11 | Writing CSS Structure for header section | rb | Done | 100 | 640
US12 | Writing CSS Structure for body section | rb | Done | 100 | 640
US13 | Writing Scripts in JS for header section | as | Done | 250 | 960
US14 | Writing Scripts in JS for body section | as | Done | 250 | 960
US15 | Animation of header section | sr | Done | 80 | 480
US16 | Animation of body section | sr | Done | 100 | 480
US17 | Writing HTML Structure for Page Background and Text(includes heading, subheading etc.) | sa | Done | 50 | 120
US18 | Writing CSS Structure for Page Background and Text(includes heading, subheading etc.) | sa | Done | 100 | 240

## Unit Test Cases
Id | Title | Acceptance test | Priority | Execution | Expected Result | Actual Result | Owner
US01 | Navigation Section | navigation() | 1 | Mannual | Navigation should appear at the top with all animations. | Navigation is successfully appearing at the top with all animations. | as
US02 | Footer Section | footer() | 2 | Mannual | Footer should appear at the bottom with all animations. | Footer is successfully appearing at the bottom with all animations. | rb
US03 | Home Page Slider Section | homePageSlider() | 3 | Mannual | An image slider should appear in the webpage body. | An image slider is successfully appearing in the webpage body. | sp
US04 | Home Page Image Buttons Section | imageButton() | 4 | Mannual | Image buttons should appear in the webpage body. | Image buttons are successfully appearing in the webpage body. | sr
US05 | Home Page Reviews Slider Section | homePageReviewSlider() | 5 | Mannual | A review slider should appear in the webpage body. | A review slider is successfully appearing in the webpage body. | sa
US06 | Navigation Section | guitarImageButtons() | 6 | Mannual | Guitar Game Navigation Item should appear at the top with all animations. | Guitar Game Navigation is successfully appearing at the top with all animations. | sp
US06 | Footer Section | guitarImageButtons() | 7 | Mannual | Guitar Game Footer should appear at the bottom with all animations. | Guitar Game Footer is successfully appearing at the bottom with all animations. | sr
US06 | Browser compatibility for normal guitar section | guitarImageButtons() | 8 | Mannual | User should be able to use normal guitar game in all screen resolutions | User is able to use normal guitar game in all screen resolutions | as
US06 | Browser compatibility for electric guitar section | guitarImageButtons() | 9 | Mannual | User should be able to use electric guitar game in all screen resolutions | User is able to use electric guitar game in all screen resolutions | rb
US06 | Animations for content | guitarImageButtons() | 10 | Mannual | A user should be able to view all animations applied to the content | A user is able to view all animations applied to the content | sa
T07.01 | Writing HTML Structure for sidebar section | paintApplicationSidebar() | 11 | Mannual | A user should be able to view all content on sidebar | A user is able to view all content on sidebar | sp
T08.01 | Writing HTML Structure for canvas section | paintApplicationCanvas() | 12 | Mannual | A user should be able to view all content on canvas | A user is able to view all content on canvas | sr
T07.02 | Writing CSS Structure for sidebar section | paintApplicationSidebar() | 13 | Mannual | A user should be able to view all styles on sidebar | A user is able to view all styles on sidebar | as
T08.02 | Writing CSS Structure for canvas section | paintApplicationCanvas() | 14 | Mannual | A user should be able to view all styles on canvas | A user is able to view all styles on canvas | rb
T07.03 | Writing Scripts in JS for sidebar section | paintApplicationSidebar() | 15 | Mannual | A user should be able to select a component on sidebar | A user is able to select a component on sidebar | sa
T08.03 | Writing Scripts in JS for canvas section | paintApplicationCanvas() | 16 | Mannual | A user should be able to draw any picture on canvas | A user is able to draw any picture on canvas | sp
T07.04 | Animation of sidebar section | paintApplicationSidebar() | 17 | Mannual | A user should be able to view all animations applied to the sidebar section | A user is able to view all animations applied to the sidebar section | sr
T08.04 | Animation of canvas section | paintApplicationCanvas() | 18 | Mannual | A user should be able to view all animations applied to the canvas section | A user is able to view all animations applied to the canvas section | as
T07.05 | Writing HTML Structure for Page Background and Text(includes heading, subheading etc.) | paintApplicationSidebar() | 19 | Mannual | A user should be able to view Page Background and Text(includes heading, subheading etc.) | A user is able to view Page Background and Text(includes heading, subheading etc.) | rb
T08.05 | Writing CSS Structure for Page Background and Text(includes heading, subheading etc.) | paintApplicationCanvas() | 20 | Mannual | A user should be able to view all styles applied to Page Background and Text(includes heading, subheading etc.) | A user is able to view all styles applied to Page Background and Text(includes heading, subheading etc.) | sa